## Sheet1
Defect ID | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
1 | Open | Nikhil | v1 | NC40 | Enter date greater than current date in DATE FIELD | An error message"Date cannot be more than current date"must shown | it does not show any error message | Medium | Medium
2 | Open | Nikhil | v1 | NC41 | Enter date with more then 2 digit in date field | An error message"DD cannot accept only two digit"is shown | it does not show any error message | Medium | Medium
3 | Open | Nikhil | v1 | NC42 | Enter grater then 31 | An error message"DD cannot be more then 31"must be shown | it does not show any error message | Medium | Medium
4 | Open | Nikhil | v1 | NC43 | Enter special character in DOB field | An error message"DD cannot have special character"must be shown | it does not show any error message | Medium | Medium
5 | Open | Nikhil | v1 | NC44 | Enter alphabet in DOB field | An error message"DD cannot have alphabet"must be shown | it does not show any error message | Medium | Medium
6 | Open | Nikhil | v1 | NC45 | Enter date with space in it | An error message"DD cannot have space"must be shown | it does not show any error message | Medium | Medium
7 | Open | Nikhil | v1 | NC46 | Do not enter value in DOB field | An error message"DD cannot be Empty"must be shown | it does not show any error message | Medium | Medium
8 | Open | Nikhil | v1 | NC47 | Enter date with sapce | An error message"DD cannot have space"must be shown | it does not show any error message | Medium | Medium
9 | Open | Nikhil | v1 | NC48 | Enter month greater than current month in date field | An error message"month cannot be more than current month''must be shown | it does not show any error message | Medium | Medium
10 | Open | Nikhil | v1 | NC49 | Enter month with more than 2 digit in date field | An error message"MM Date can not have more than 2 digit in MM field"must shown | it does not show any error message | Medium | Medium
11 | Open | Nikhil | v1 | NC50 | Enter value 0 in MM field | An error message"MM cannot have 0"must be shown | it does not show any error message | Medium | Medium
12 | Open | Nikhil | v1 | NC51 | Enter negative numbers | An error message"MM Cannot have less than 1"must be shown | it does not show any error message | Medium | Medium
13 | Open | Nikhil | v1 | NC52 | Enter grater then 12 | An error message"MM cannot have greater than 12"must be shown | it does not show any error message | Medium | Medium
14 | Open | Nikhil | v1 | NC53 | Enter special in MM field | An Error message"MM cannot have special character"must e shown | it does not show any error message | Medium | Medium
15 | Open | Nikhil | v1 | NC54 | Enter alphabet in MM field | An error message"MM cannot have alphabet"must be shown | it does not show any error message | Medium | Medium
16 | Open | Nikhil | v1 | NC55 | Enter MM with space in it | An error message"MM cannot have space"must be shown | it does not show any error message | Medium | Medium
17 | Open | Nikhil | v1 | NC56 | Don not enter value in MM field | An error message"MM cannot be empty"must be shown | it does not show any error message | Medium | Medium
18 | Open | Nikhil | v1 | NC57 | Enter date with space in it | An error message"MM cannot have blank space"must be shown | it does not show any error message | Medium | Medium
19 | Open | Nikhil | v1 | NC58 | Enter the greater than 4 digit in YYYY | AN error message " YYYY are not allowed greater than 4 digit " must be shown | it does not show any error message | Medium | Medium
20 | Open | Nikhil | v1 | NC60 | Enter negative number | An error message"YYYY cannot have less than 1"must be shown | it does not show any error message | Medium | Medium
21 | Open | Nikhil | v1 | NC61 | Enter special character in YYYY field | An error message"YYYY cannot have special character"must be shown | it does not show any error message | Medium | Medium
22 | Open | Nikhil | v1 | NC62 | Enter alphabet in YYYY field | An error message"YYYY cannot have alphabet"must be shown | it does not show any error message | Medium | Medium
23 | Open | Nikhil | v1 | NC63 | Enter YYYY with blank space in it | An error message"YYYY Cannot have blank space"must be shown | it does not show any error message | Medium | Medium
24 | Open | Nikhil | v1 | NC64 | Do not enter value in YYYY field | An error message"YYYY cannot be empty"must be shown | it does not show any error message | Medium | Medium
25 | Open | Nikhil | v1 | NC65 | Enter date with space in it | An error message"YYYY Cannot have blank space"must be shown | it does not show any error message | Medium | Medium
26 | Open | Nikhil | v1 | NC66 | Enter value 0 in YYYY | An error message"YYYY Cannot contain 0"must be shown | it does not show any error message | Medium | Medium
27 | Open | Nikhil | v1 | NC68 | Enter greater than 1 dot in Email field | An error message"Enter valid Email address"must be shown | It does not show any error message | Medium | Medium
28 | Open | Nikhil | v1 | NC72 | Enter email address with space in it | An error message"Email cannot have space"must be shown | It does not show any error message | Medium | Medium
29 | Open | Nikhil | v1 | NC77 | Enter two @ sign | an error message " Enter valid Email ID " must be shown | It does not show any error message | Medium | Medium
30 | Open | Nikhil | v1 | NC80 | enter previous use email id | an error message " email id is already use " must be shown | it does not show any error message | Medium | Medium
31 | Open | Nikhil | v1 | EC2 | enter spaces between two number in customer id field | An error message " spaces are not allowed " must be shown | It does not show any error message | Medium | Medium
32 | Open | Nikhil | v1 | DC2 | enter space between two number in customer id field | An error message " spaces are not allowed " must be shown | It does not show any error message | Medium | Medium
33 | Open | Nikhil | v1 | DC10 | click on sumbit button | It should accept it and successfully move on to the next field | not delected customer successfully | Medium | Medium
34 | Open | Nikhil | v1 | NA2 | enter space btween two number in customer id field | An error message " spaces not allowed" must shown | It does not show any erorr message | Medium | Medium
35 | Open | Nikhil | v1 | NA19 | Initial deposit field can not be less then 500 | An error message"Initial deposit cannot have less than given limit"must be shown | It dosent show any error message | Medium | Medium
36 | Open | Nikhil | v1 | NA20 | Initial deposit field can not be more then 20000 | An error message"Initial deposit cannot have more than given limit"must be shown | It dosent show any error message | Medium | Medium
37 | Open | Nikhil | v1 | NA22 | click on submit button | It should accept it and successfully move on to the next field | new account not generated | Medium | Medium
38 | Open | Nikhil | v1 | EA2 | enter the space between two number in account no field | an error message " spaces are not allowed" must be shown | An error message " character are not allowed " is shown | Medium | Medium
39 | Open | Nikhil | v1 | EA5 | enter first letter blank in account no field | An error message " first character blank are not allowed" must shown | An error message " character are not allowed " is shown | Medium | Medium
40 | Open | Nikhil | v1 | EA11 | click on sumbit button | It should accept it and successfully move on to the next field | it must not be accepted | Medium | Medium
41 | Open | Nikhil | v1 | DA2 | enter the space between two number in account no field | An error message " space are not allowed " must be shown | An error message " character are not allowed " is shown | Medium | Medium
42 | Open | Nikhil | v1 | DA6 | enter first character blank in account no field | An error message " account no must not have first character blank " must be shown | An error message " character are not allowed " is shown | Medium | Medium
43 | Open | Nikhil | v1 | DA11 | click on sumbit button | It should accept it and successfully move on to the next field | not deleted succssfully | Medium | Medium
44 | open | nikhil | V1 | BE2 | enter the space between two number | it must be accepted and move successfully on next field | an error message " character are not allowed " is must shown | medium | medium
45 | open | nikhil | V1 | BE5 | enter first letter empty in account no field | an error message " first letter emtpty are not allowed in account no field " must shown | an error message " character are not allowed " is must shown | medium | medium
46 | open | nikhil | V1 | BE8 | click the submit button | it must be accepted and move successfully on next field | not open successfully | medium | medium
47 | Open | Nikhil | v1 | MS3 | enter spaces betwwen two number in account no field | An error message " spaces are not allowed " must be shown | An error message " character are not allowed " is shown | Medium | Medium
48 | Open | Nikhil | v1 | MS6 | enter first letter blank in account no filed | An error message " account no must no have first character empty" must be shown | An error message " character are not allowed " is shown | Medium | Medium
49 | Open | Nikhil | v1 | MS11 | click on sumbit button | It should accept it and successfully move on to the next field | not open mini statement | Medium | Medium
50 | Open | Nikhil | v1 | CS3 | enter space between two number in account no field | An error message " spaces are not allowed " must be shown | An error message"Charater are not allow"is shown | Medium | Medium
51 | Open | Nikhil | v1 | CS6 | enter first letter blank in account no field | An error message " account no must not have first character blank " must be shown | An error message"Charater are not allow"is shown | Medium | Medium
52 | Open | Nikhil | v1 | CS8 | enter the less than two digit number in FROM DATE field | an error message " less than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
53 | Open | Nikhil | v1 | CS9 | enter the greter than two digit number in FROM DATE field | an error message " greter than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
54 | Open | Nikhil | v1 | CS11 | enter the less than two digit number in FROM DATE field | an error message " less than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
55 | Open | Nikhil | v1 | CS12 | enter the greter than two digit number in FROM DATE field | an error message " greter than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
56 | Open | Nikhil | v1 | CS14 | enter the less than four digit number in FROM DATE field | an error message " less than four digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
57 | Open | Nikhil | v1 | CS15 | enter the greter than four digit number in FROM DATE field | an error message " greter than four digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
58 | Open | Nikhil | v1 | CS17 | enter the date greter than 31 in FROM DATE Field | an error message " greter than 31 cannot be accepted" must shown | no error message is shown | Medium | Medium
59 | Open | Nikhil | v1 | CS18 | enter the date less than 1 in FROM DATE field | an error message " less than 1 cannot be accepted" must shown | no error message is shown | Medium | Medium
60 | Open | Nikhil | v1 | CS19 | enter the date greter than 29 FEB in FROM DATE field | an error message " greter than 29 cannot be accepted" must shown | no error message is shown | Medium | Medium
61 | Open | Nikhil | v1 | CS21 | enter the date greter than 28 FEB MONTH in FROM DATE field | an error message " greter than 28 cannot be accepted" must shown | no error message is shown | Medium | Medium
62 | Open | Nikhil | v1 | CS23 | enter the date greter than 12 in FROM DATE FIELD | an error message " greter than 12 cannot be accepted" must shown | no error message is shown | Medium | Medium
63 | Open | Nikhil | v1 | CS25 | enter the number less than 1 in FROM DATE field | an error message " less than 1 cannot be accepted" must shown | no error message is shown | Medium | Medium
64 | Open | Nikhil | v1 | CS26 | enter the character in FROM DATE field | an error message " character cannot be accepted" must shown | no error message is shown | Medium | Medium
65 | Open | Nikhil | v1 | CS27 | enter the special character in FROM DATE field | an error message " special character cannot be accepted" must shown | no error message is shown | Medium | Medium
66 | Open | Nikhil | v1 | CS28 | do not enter value in FROM DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
67 | Open | Nikhil | v1 | CS29 | do not enter date in FROM DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
68 | Open | Nikhil | v1 | CS30 | do not enter month in FROM DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
69 | Open | Nikhil | v1 | CS31 | do not enter year in FROM DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
70 | Open | Nikhil | v1 | CS32 | ENTER the from date greter than to date | an error message " FROM DATE not greater than TO date " must shown | no error message is shown | Medium | Medium
71 | Open | Nikhil | v1 | CS34 | enter the less than two digit number in TO DATE field | an error message " less than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
72 | Open | Nikhil | v1 | CS35 | enter the greter than two digit number in TO DATE field | an error message " greter than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
73 | Open | Nikhil | v1 | CS37 | enter the less than two digit number in TO DATE field | an error message " less than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
74 | Open | Nikhil | v1 | CS38 | enter the greter than two digit number in TO DATE field | an error message " greter than two digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
75 | Open | Nikhil | v1 | CS40 | enter the less than four digit number in TO DATE field | an error message " less than four digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
76 | Open | Nikhil | v1 | CS41 | enter the greter than four digit number in TO DATE field | an error message " greter than four digit number cannot be accepted" must shown | no error message is shown | Medium | Medium
77 | Open | Nikhil | v1 | CS43 | enter the date greter than 31 in TO DATE Field | an error message " greter than 31 cannot be accepted" must shown | no error message is shown | Medium | Medium
78 | Open | Nikhil | v1 | CS44 | enter the date less than 1 in TO DATE field | an error message " less than 1 cannot be accepted" must shown | no error message is shown | Medium | Medium
79 | Open | Nikhil | v1 | CS45 | enter the date greter than 29 in TO DATE field | an error message " greter than 29 cannot be accepted" must shown | no error message is shown | Medium | Medium
80 | Open | Nikhil | v1 | CS47 | enter the date greter than 28 in TO DATE field | an error message " greter than 28 cannot be accepted" must shown | no error message is shown | Medium | Medium
81 | Open | Nikhil | v1 | CS49 | enter the date greter than 12 in TO DATE FIELD | an error message " greter than 12 cannot be accepted" must shown | no error message is shown | Medium | Medium
82 | Open | Nikhil | v1 | CS51 | enter the number less than 1 in TO DATE field | an error message " less than 1 cannot be accepted" must shown | no error message is shown | Medium | Medium
83 | Open | Nikhil | v1 | CS52 | enter the character in TO DATE field | an error message " character cannot be accepted" must shown | no error message is shown | Medium | Medium
84 | Open | Nikhil | v1 | CS53 | enter the special character in TO DATE field | an error message " special character cannot be accepted" must shown | no error message is shown | Medium | Medium
85 | Open | Nikhil | v1 | CS54 | do not enter value in TO DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
86 | Open | Nikhil | v1 | CS55 | do not enter date in TO DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
87 | Open | Nikhil | v1 | CS56 | do not enter month in TO DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
88 | Open | Nikhil | v1 | CS57 | do not enter year in TO DATE field | an error message " blank space cannot be accepted" must shown | no error message is shown | Medium | Medium
89 | Open | Nikhil | v1 | CS59 | ENTER the TO DATE less than FROM date | an arror message " TO DATE must be greater than FROM DATE" must shown | no error message is shown | Medium | Medium
90 | Open | Nikhil | v1 | CS60 | Do not Enter value in ammount lower limit field | An error message"Amount lower limit cannot be empty"Must be shown | It dosent show any error message | Medium | Medium
91 | Open | Nikhil | v1 | CS64 | Enter first character blank space in amount lower limit field | An error message"First character cannot have space"must be shown | It dosent show any error message | Medium | Medium
92 | Open | Nikhil | v1 | CS65 | Enter less then 500 in amount lower limit field | An error message"Account lower limit is 500"must be shown | It dosent show any error message | Medium | Medium
93 | Open | Nikhil | v1 | CS67 | DO not enetr any value in number of transaction firld | An error message"Number of transation cannot be empty"must be shown | It does not show any error message | Medium | Medium
94 | Open | Nikhil | v1 | CS70 | Enter first character blank space in number of transaction field | An error message"First character cannot have space"must be shown | It does not show any error message | Medium | Medium
95 | Open | Nikhil | v1 | CS75 | click on sumbit button | It should accept it and successfully move on to the next field | no open statement page | Medium | Medium